## Cover
Project Services Estimate
Project ID | 1830
Client | Sample Client

## Process
Discipline | Deliverable | Activity Name | Qty | Engineer Hrs | Designer Hrs | Checker Hrs | PM Hrs | Total Hrs | Notes
Project Services | Project Services Estimate | Develop - Project Services Estimate (PSE) | 1 | 12 | 6 | 3 | 2 | 23 | 1830 sample line
Process | PFD | Develop - PFD | 1 | 40 | 20 | 10 | 5 | 75
Process | P&ID | Develop - P&ID | 1 | 80 | 40 | 20 | 8 | 148
I&C | Preliminary Datasheets | Develop - Preliminary Datasheets | 1 | 30 | 25 | 8 | 2 | 65